# 18–36 Month Immigration & Research Roadmap

## Ardia Health Labs | Rambabu Vadlamudi (EB-1A) & Manasa Jampani (EB-2 NIW)

## Starting: July 2026

Design philosophy: This roadmap reads as two researchers documenting their company’s problem domain — not two founders accumulating visa evidence. Every action item has an organic business reason independent of immigration. The publication cadence mirrors how a working researcher documents one domain at a time.

## How to Read This Roadmap

| Symbol | Meaning |
| --- | --- |
| RAM | Rambabu Vadlamudi action |
| MAN | Manasa Jampani action |
| BOTH | Joint action |
| ★ | High-priority immigration milestone |
| ⚡ | Time-sensitive (do within the week) |

Alternating publication rhythm: Ram publishes ODD months; Manasa publishes EVEN months. Never two papers in the same month — organic researchers don’t do that. LinkedIn articles fill the gaps between papers.

## Phase 1: Establish Publication Record (Jul 2026 – Dec 2026)

### July 2026 — Ram’s Launch Month

Week 1 (⚡ Action now): - RAM: ★ Submit Paper 1 (DGP Architecture) to arXiv cs.AI — this establishes Criterion 6 (publications) and anchors the entire EB-1A filing - Category: cs.AI primary; cs.IR and q-bio.QM secondary - Endorser needed if first submission: email a cs.AI endorser (list in arXiv guide) - Simultaneous: start JAMIA submission process (peer-reviewed journal record follows arXiv) - RAM: ★ Email editor@jamia.org requesting peer reviewer registration (Criterion 4 — judging) - RAM: Publish LinkedIn article 1: “Why 65% of Denied Lab Claims Are Never Appealed — And How AI Can Change That” - 800–1,000 words; first-person authentic voice; cites XiFin 2024 and JAMA 2025 data - Post to LinkedIn; screenshot URL, date, view count for petition evidence

Week 2–4: - RAM: Monitor arXiv — paper goes live in 24–48 hrs; save the arXiv URL and timestamp ★ - RAM: Apply to Forbes Technology Council (forbestechcouncil.com) — Criterion 2 (membership) - RAM: Apply to AMIA membership (amia.org) — Criterion 2 + signals to judging targets - BOTH: Apply for HIMSS membership — direct healthcare IT credential for both

Month-end check: Paper 1 is on arXiv. LinkedIn article is posted. JAMIA reviewer application is submitted.

### August 2026 — Manasa’s Launch Month

Week 1–2: - MAN: ★ Post Paper 4 (Payer AI Black Box) to medRxiv — immediate publication record for NIW - Category: Health Informatics - Save medRxiv DOI the moment it goes live (24–48 hrs) — this is her first immigration evidence document - Simultaneous: begin NEJM AI submission (use cover letter template in submission guide) - MAN: Publish LinkedIn article 1: “What 5 Years on the Payer Side Taught Me About Why Your Lab Claims Get Denied” - First-person CEO voice; 800–1,000 words; reference Paper 4 thesis accessibly - Screenshot for NIW evidence

Week 3–4: - MAN: Apply to AMIA membership (amia.org) - MAN: Apply to HIMSS membership (himss.org) - MAN: Email Georgetown JAMA 2025 study PI — introduce yourself; note Paper 4 cites their research; begin expert witness relationship (do NOT ask for letter yet — too early) - RAM: Follow up on JAMIA reviewer registration if no response

Month-end check: Paper 4 is on medRxiv. LinkedIn articles by both founders are live.

### September 2026 — Ram’s Second Paper Month

Week 1–2: - RAM: ★ Submit Paper 6: PAMA 2027 + AI Solutions to arXiv - Use academic term “PAMA 2027 Medicare reimbursement reduction” — NOT “PAMA cliff” - Title: “Artificial Intelligence-Driven Revenue Protection for Independent Clinical Laboratories Under PAMA 2027 Medicare Reimbursement Reductions” - This paper = Criterion 6 paper 2; plus the policy angle opens press coverage opportunities - RAM: Publish LinkedIn article 2: “Building Compliant Healthcare AI: What Texas SB 1188 Actually Requires” - References Paper 3 (AI Governance); establishes regulatory expertise

Week 3–4: - RAM: Pitch Becker’s Hospital Review: DFW AI founder solving $12B lab billing crisis - Email: editors@beckershealthcare.com - Hook: PAMA 2027 is 18 months away; labs need AI now; Ram is building it in DFW - RAM: Apply to ACLA membership (acla.com) — lab industry credentialing - BOTH: Begin building ResearchGate profiles — link arXiv and medRxiv papers; increases discoverability

Month-end check: Paper 6 on arXiv. Becker’s pitch sent. Two papers live for Ram.

### October 2026 — Manasa’s Second Paper Month

Week 1–2: - MAN: ★ Submit Paper M1: ACO + Independent Lab AI Optimization to arXiv - Title: “Artificial Intelligence-Optimized Laboratory Utilization in Accountable Care Organization Shared Savings Programs: A Framework for Independent Clinical Laboratories” - Angle: Manasa’s Interwell Health + ACO operations expertise; first paper combining ACO + independent lab + AI - Target journal: Journal of Healthcare Management (after arXiv) - MAN: Publish LinkedIn article 2: “The ACO Opportunity Independent Labs Are Missing” - CEO business angle; 700–900 words; references ACO shared savings data

Week 3–4: - MAN: Email XiFin industry relations team — introduce Paper 4 (citing their 2024 report); begin relationship - MAN: Contact BSWQA (Baylor Scott & White Quality Alliance) — initial conversation about ACO + lab collaboration (expert witness cultivation, not yet asking for letter) - RAM: Check Forbes Tech Council application status; follow up if no response

Month-end check: Paper M1 on arXiv. Manasa has 2 papers live. ACO expert witness pipeline initiated.

### November 2026 — Ram’s Third Paper Month

Week 1–2: - RAM: ★ Submit Paper 8: Toxicology RCM AI (ToxIQ™) to arXiv - Title: “ToxIQ: An AI-Driven Revenue Cycle Management Framework for Clinical Toxicology and Urine Drug Screening Claim Compliance” - Target journal: Clinical Chemistry or JALM - This is the FIRST academic paper on AI for UDS billing — establishes priority - RAM: Publish LinkedIn article 3: “The PAMA Cliff Is Coming in 2027. Here’s What Independent Labs Need to Do Now” - Reference Paper 6; educates lab industry on PAMA AI solutions

Week 3–4: - RAM: If Forbes Tech Council approved: ★ write first member article on DGP architecture - Forbes TC articles build Criterion 3 (press coverage) evidence - RAM: Apply for DFW Tech & Innovation Award — search for 2026–2027 cycle timing - RAM: Submit abstract to AMIA 2027 Annual Symposium (Dec 2026 deadline) - Abstract on DGP architecture; conference presentation = Criterion 4 (judging) + Criterion 3 (press)

Month-end check: Paper 8 on arXiv. Ram has 3 papers live. AMIA abstract submitted.

### December 2026 — Manasa’s Third Paper Month

Week 1–2: - MAN: ★ Submit Paper M2: Payer AI Accountability & Fairness to arXiv - Title: “Algorithmic Accountability in Prior Authorization Denial Systems: An Insider Clinical Operations Analysis of Payer AI Configuration and Independent Laboratory Disparities” - Target journal: Health Affairs - Must differentiate from Health Affairs 2025 (external critique) — Manasa’s is INSIDER analysis - MAN: Publish LinkedIn article 3: “PAMA 2027: Why the $12 Billion Lab Billing Crisis Is Also a Healthcare Equity Crisis” - Policy + equity angle; references both Paper 4 and Paper M2

Week 3–4: - MAN: Follow up with Georgetown PI — share Paper 4 medRxiv link; offer to discuss findings - BOTH: ★ Quarterly evidence review — photograph/screenshot all LinkedIn article stats; save arXiv view counts; compile Google Scholar citations check

Month-end check (Dec 2026 — 6-month milestone): - Ram: 3 papers (Papers 1, 6, 8) + 3 LinkedIn articles - Manasa: 3 papers (Papers 4, M1, M2) + 3 LinkedIn articles - Both: AMIA member; HIMSS member - Ram: Forbes Tech Council (if approved); JAMIA reviewer (if approved)

## Phase 2: Build Expert Recognition & File Petitions (Jan 2027 – Jun 2027)

### January 2027 — Ram’s Fourth Paper Month

Week 1–2: - RAM: Publish LinkedIn article 4: “MolDX Compliance: The Hidden Billing Complexity Killing Independent Lab Revenue” - Previews Paper 9 (MolDX Compliance AI); technical depth signals expertise - RAM: Follow up on all expert witness targets — share Paper 1 and Paper 6 (now on arXiv) - Email Georgetown PI: “Our Paper 1 on DGP architecture cites your JAMA research…” - Email XiFin: “We have 3 arXiv papers now; would you be willing to serve as expert witness?”

Week 3–4: - RAM: ★ Begin preparing EB-1A petition package with immigration attorney - Criteria to file with: C5 (Original Contributions — DGP architecture), C8 (Leading Role — Founder), C6 (Publications — 3 arXiv papers minimum) - Supporting: Forbes TC membership, JAMIA reviewer, AMIA membership - Attorney review needed: 4–6 weeks; have all evidence ready by February - RAM: Apply to NIH SBIR Study Section (csr.nih.gov) — rolling deadline; Criterion 4 boost

Month-end target: EB-1A petition preparation underway. Expert witness outreach active.

### February 2027 — Manasa’s Fourth Paper Month

Week 1–2: - MAN: ★ Submit Paper M3: Renal Care + Molecular Diagnostics Billing to arXiv - Title: “Revenue Cycle Complexity in Renal Care Molecular Diagnostics: An AI Framework for Independent Laboratory Billing Compliance” - Draws on Manasa’s Interwell Health domain knowledge; target: Clinical Chemistry - MAN: Publish LinkedIn article 4: “Building Ardia Health: What It Takes to Flip the Script on Payer AI Denial Systems” - CEO narrative; authentic journey; reinforces NIW P2 (unique positioning)

Week 3–4: - MAN: ★ Begin preparing EB-2 NIW petition package with immigration attorney - Criteria: P1 (national importance), P2 (payer-insider unique positioning), P3 (urgent need) - Evidence needed: Paper 4 medRxiv + NEJM AI status; Papers M1 + M2; Georgetown expert witness; XiFin expert witness - EB-2 NIW is typically filed 6–12 months after supporting evidence is in place - MAN: Request expert witness letter from Georgetown PI (if relationship established via prior emails) - Use Template 1 from expert_witness_letter_templates.md - First target: Prong 1 (national importance) letter

Month-end target: NIW petition preparation underway. First expert witness letter requested.

### March 2027 — Ram’s Fifth Paper Month

Week 1–2: - RAM: ★ Submit Paper 9: MolDX Compliance AI to arXiv - Title: “Deterministic AI Encoding of MolDX Program Compliance Requirements for Molecular Diagnostic Billing” - Target: JAMIA (cs.AI paper with clinical informatics application) - FIRST published framework for MolDX compliance AI - RAM: Publish LinkedIn article 5: “Why Deterministic Rules Must Come Before LLMs in Healthcare Administrative AI” - Technical thought leadership; establishes DGP architecture in public record

Week 3–4: - RAM: ★ File EB-1A petition (if attorney confirms readiness) - Minimum filing criteria: C5 + C8 + C6 (3 papers arXiv = C6) - Stronger: add Forbes TC (C2) + JAMIA reviewer (C4) if approved - Include Paper 1 JAMIA peer review status if available - File with premium processing ($2,805 fee) for 15-business-day adjudication - RAM: Apply to Fast Company Most Innovative Companies (October–November cycle opens Q4 2026; follow up)

Month-end target (Q1 2027 milestone): EB-1A petition filed OR ready to file within 30 days.

### April 2027 — Manasa’s Fifth Paper Month

Week 1–2: - MAN: ★ Submit Paper M4: Value-Based Care Lab Economics to arXiv - Title: “Value-Based Care Economics for Independent Clinical Laboratories: AI-Optimized Test Utilization in ACO Shared Savings Frameworks” - Target: American Journal of Managed Care - MAN: Publish LinkedIn article 5: “Renal Care + Molecular Diagnostics: The Underappreciated Billing Complexity” - References Paper M3; demonstrates domain expertise in nephrology + diagnostics

Week 3–4: - MAN: ★ Request expert witness letter from XiFin Research Principal (Prong 1 + Prong 3 letter) - Use Template 2 (ACO/healthcare operations variant adapted for industry research) - MAN: ★ File EB-2 NIW petition (if attorney confirms readiness) - Target: File by April–May 2027 (9 months into publication record) - Minimum evidence: Papers 4 + M1 + M2 + M3 on arXiv/medRxiv; 2 expert witness letters - Priority date established at filing; premium processing option available

Month-end target (Q2 2027 milestone): NIW petition filed OR ready within 30 days.

### May 2027 — Ram’s Sixth Paper Month

Week 1–2: - RAM: Publish LinkedIn article 6: “Six Months of ToxIQ™: What We Learned Running AI-Driven Toxicology Claim Recovery” (if pilot data available) - OR: “Independent Lab Survival Guide: Three Strategies Before PAMA 2027” - RAM: Submit Paper 10: Behavioral Health Billing AI to arXiv - Title: “BehaviorIQ: An AI Framework for Claim Compliance and Denial Recovery in Behavioral Health and Addiction Medicine Billing” - First paper on AI for behavioral health billing; cites 30% denial rate vs. 19% for other specialties

Week 3–4: - RAM: If EB-1A RFE arrives: respond with evidence of Criteria that have strengthened (AMIA conference, press coverage, pilot outcomes) - RAM: Check on JAMIA Paper 1 peer review status; follow up if >6 months since submission

### June 2027 — Manasa’s Pilot Outcomes Month

Week 1–2 (if pilot data available): - MAN: ★ Submit Paper M5: Pilot Outcomes — CEO Perspective to arXiv → JAMIA - This is the strongest evidence paper in the entire series — real data showing DGP platform outcomes - Title: “AI-Driven Revenue Cycle Management in Independent Clinical Laboratory Billing: 12-Month Outcomes of the Ardia DGP Pilot Program” - Co-authored with Ram (Ram as senior/corresponding author; Manasa as CEO perspective co-author) - BOTH: Publish joint LinkedIn article: “Six Months of Ardia: What We Built and What the Data Shows”

Week 3–4: - BOTH: ★ Notify expert witnesses of Pilot Paper — share preprint; update them on petition status - BOTH: Pitch STAT News (tips@statnews.com) with pilot outcomes data - Hook: First real-world data on AI for independent lab revenue recovery; PAMA 2027 urgency - This = Criterion 3 press coverage (national healthcare media)

Month-end check (12-month milestone, Jun 2027):

| Metric | Ram | Manasa |
| --- | --- | --- |
| Papers on arXiv/medRxiv | 5–6 | 5–6 |
| LinkedIn articles | 6 | 6 |
| Expert witness letters | 1–2 obtained | 2 obtained |
| Peer-reviewed journals | 1 (JAMIA, if accepted) | Pending |
| EB petition status | Filed (Mar 2027) or pending | Filed (Apr 2027) or pending |

## Phase 3: Strengthen Evidence & Respond to Adjudication (Jul 2027 – Jun 2028)

### Continuing Publication Pattern (Jul–Dec 2027)

Both founders continue alternating monthly cadence. Priority papers for this period:

Ram (odd months): - Paper 11: Pilot Outcomes Follow-Up (6-month data update, if Paper M5 filed earlier) - Paper 12: PGx Revenue Cycle AI for Independent Labs (Paper 7 from original list) - Policy brief: PAMA 2027 and the Case for AI Revenue Infrastructure (Health Affairs submission)

Manasa (even months): - Paper M6: Payer AI Transparency Policy Brief (Health Affairs) - Paper M7: 42 CFR Part 2 Compliance AI for Addiction Medicine Billing (extend BehaviorIQ™) - Update/resubmit Papers to peer-reviewed journals if arXiv versions have accumulated citations

### Expert Witness Network (Ongoing)

| Target | Action | Timing |
| --- | --- | --- |
| Georgetown PI | ★ Obtain letter if not done by Mar 2027 | Apr 2027 |
| XiFin Principal | Obtain letter after Paper 4 published in journal | Q3 2027 |
| BSWQA / SWHR ACO Executive | Obtain letter after pilot data available | Q3 2027 |
| AMIA editorial board member | Approach after AMIA 2027 conference | Q4 2027 |
| UT Southwestern Informatics Faculty | Cite Paper 1 → approach for expert letter | Q2 2027 |

### Press Coverage Strategy (Ongoing)

| Publication | Pitch | Timing |
| --- | --- | --- |
| Becker’s Hospital Review | DFW AI startup + PAMA urgency | Sep 2026 (already targeted) |
| MedCity News | PAMA 2027 + AI startup angle | Oct 2026 |
| Dallas Business Journal | DFW healthcare AI startup | Q4 2026 |
| STAT News | Pilot outcomes data | Jun 2027 |
| Modern Healthcare | CEO profile post-pilot | Q3 2027 |
| Healthcare IT Today | Technical: DGP architecture | After Paper 1 in JAMIA |

## Phase 4: Citation Network & Scale (Jul 2028 – Jun 2029)

By this phase, both founders have 8–10 papers each. The citation network begins to build: - Papers 6–10 cite Paper 1 (DGP architecture as foundational) - Papers M1–M5 cite Paper 4 (payer AI black box as foundational) - Others in the field begin citing Ardia papers - Google Scholar profiles show citation counts accumulating

### 2028 Publication Strategy

The publication goal shifts from establishing white spaces to EXTENDING established frameworks: - “DGP 2.0: 18-Month Performance Analysis of the Three-Layer Revenue Architecture” - “Predictive Denial Prevention: Validating the ML Layer of DGP Against National Claims Databases” - “Independent Laboratory Survival Under PAMA: Evidence from the First AI-Driven Billing Platform”

Each new paper cites prior published work — creating a self-reinforcing citation network that is itself evidence of scholarly impact (Criterion 6 extended).

## No-RFE Strategy: Filing Checklist

### Ram’s EB-1A — File When ALL of These Are True:

- ☐ Paper 1 on arXiv (establishes C6 AND shows original contribution C5) ← July 2026

- ☐ Paper 6 on arXiv (second C6 paper) ← September 2026

- ☐ Paper 8 on arXiv (third C6 paper — minimum 3 for strong C6) ← November 2026

- ☐ JAMIA peer reviewer approved (C4 — judging) ← Target: October 2026

- ☐ AMIA or Forbes Tech Council membership confirmed (C2) ← Target: October 2026

- ☐ At least 1 press mention in named publication (C3) ← Target: October–November 2026

- ☐ Immigration attorney review complete

- ☐ 3 expert witness letters obtained (1 lab director, 1 academic, 1 industry)

Target filing window: March 2027 (9 months of publication record)
Minimum filing window: January 2027 (6 months — possible but weaker press/judging evidence)

### Manasa’s EB-2 NIW — File When ALL of These Are True:

- ☐ Paper 4 on medRxiv ← August 2026

- ☐ Paper M1 on arXiv (second paper) ← October 2026

- ☐ Paper M2 on arXiv (third paper) ← December 2026

- ☐ Paper M3 on arXiv (fourth paper) ← February 2027

- ☐ medRxiv DOI saved and Google Scholar-indexed

- ☐ 2 expert witness letters obtained (Georgetown PI + XiFin or ACO executive)

- ☐ Immigration attorney review complete

- ☐ Dhanasar analysis attorney-reviewed and finalized

Target filing window: April 2027 (9 months of publication record)
Minimum filing window: February 2027 (6 months — possible but stronger with 4 papers)

## Why This Won’t Trigger RFEs

On publication cadence: - One paper per month ALTERNATING looks like two researchers at a company who each have their own research portfolio. It does NOT look like a coordinated visa operation. - LinkedIn articles in non-paper months look like authentic thought leadership, not manufactured evidence.

On originality: - All 6 confirmed white spaces have been systematically searched (see research_gaps.md). No examiner can find prior art because there is none. - DGP architecture is Ram’s original invention. “Deterministic-Generative-Predictive” is not a term in prior literature.

On expert witnesses: - The relationship-building approach (cite their work → share your preprint → have a conversation → ask for letter) looks authentic because it IS authentic. Examiners can tell when letters were written by people who actually know the petitioner’s work.

On the national importance argument: - $10–12B quantified problem + 35.3% denial rate (XiFin 2024, 20M+ claims) + 2.76× disparity (JAMA 2025) + 7,000 labs at risk + PAMA 2027 urgency = a documented national healthcare infrastructure crisis, not a speculative claim.

On the “not merely a green card” appearance: - The platform (Ardia Health Labs) is a functioning company with pilot customers. - The papers address real products (ToxIQ™, MolecuIQ™, AcoIQ™, BehaviorIQ™). - The publication topics are exactly what a co-founder would document as they build these products. - A USCIS examiner reading Paper 8 on Toxicology Billing AI will see it as “this person built ToxIQ™ and is documenting it” — not “this person is filling a visa checklist.”

## Timeline Summary Visual

2026                                    2027
Jul  Aug  Sep  Oct  Nov  Dec  Jan  Feb  Mar  Apr  May  Jun
RAM  MAN  RAM  MAN  RAM  MAN  RAM  MAN  RAM  MAN  RAM  MAN
P1   P4   P6   M1   P8   M2   P9   M3  P10   M4  P5★  M5★
                                    [File EB-1A]
                                              [File NIW]

★ P5 and M5 = Pilot outcomes papers (require real pilot data from Q2 2026 launch)

2027–2028                              2028–2029
Jul  Aug  Sep  Oct  Nov  Dec  ...      Jan–Dec 2029
RAM  MAN  RAM  MAN  RAM  MAN           4–6 papers each
                                       citing prior work
                                       Citation network matures
                                       Appeal/RFE responses if needed

## Monthly Maintenance Checklist (Do Every Month)

- ☐ Screenshot all new LinkedIn article stats (views, reactions, shares)

- ☐ Check Google Scholar for new citations on any published paper

- ☐ Check arXiv view count for all papers

- ☐ Save any email or social media mentions of your work

- ☐ Update JAMIA / AMIA / NIH reviewer application status

- ☐ Review any press pitches sent — follow up if >3 weeks without response

- ☐ Keep a single document with all dated evidence items — attorney will need this

For paper format standards, see: immigration/paper_format_guide.md
For individual skill trackers, use: /ram-eb1a and /manasa-eb2niw skills
For confirmed white space research: immigration/research_gaps.md